## Summary
FundacjaQ - Client Requirements vs. Implementation Gap Analysis
Based on client meeting notes (Spotkanie 1, 2, 4, 5) compared against the map-and-resources branch.
Solid / on-track: | Map, alerts, non-crisis events, geocoding, invite-only auth, audit logging, reCAPTCHA, GDPR-minimal data.
Biggest gaps vs. the client's stated MVP priorities (map + two-layer comms + needs/resources + roles):
- Resource Matrix workflow (allocation, delivery confirmation, return-to-pool) - essentially unbuilt
- Task / Kanban board - 0% implemented, no Task model exists
- Two-layer communication (admin directives + chat) - no Comment/Message model exists
Also missing: | Organization/role verification (KRS check, dual-admin approval, per-alert coordinator/transfer).
Quick wins: | Forced password change on first login; admin unlock button for locked accounts - both explicit client action items, cheap to add.

## Gap Analysis
# | Feature / Requirement | Current Status | Client Expectation | Current Implementation | Action Required
1 | Alert map (pins, tiles, popups) | Completed | Map view with event pins, tile/card view, filter by urgency & active/completed status | AlertMap.tsx + AlertsMapView.tsx fully implement pins, tiles, filters | None
2 | One-click alert update/revoke | Completed | Single-click ability to update or withdraw a communique (e.g. "already have enough water") | AlertActions.tsx -> PATCH /api/alerts/[id] sets RESOLVED/CANCELLED/reactivate | None
3 | Severity levels | Completed | Low/Medium/High risk tiers (client also floated a 4th "global" tier) | Severity enum: LOW, MEDIUM, HIGH, CRITICAL - 4 levels | None (confirm labeling matches intent)
4 | Alert categories (Powodz/Pozar/Wichura/Awaria + custom) | Needs Change | Client proposed 4 categories + free-text "own category," but explicitly left this unconfirmed pending further client input | AlertCategory enum has different fixed set: HYDROLOGICAL, ROAD, HUMANITARIAN, FIRE, INFRASTRUCTURE, GENERAL - no custom/free-text category option | Confirm final category list with client; add "custom category" free-text fallback if still desired
5 | Non-crisis "everyday events" (dual-use, festyn/koncert/etc.) | Completed | Separate toggle for daily/non-crisis events (concerts, festivals) vs crisis alerts, with lighter/positive iconography | AlertKind enum (ALERT/EVENT) + AlertsMapView.tsx toggle + EVENT_CATEGORIES (Festival, Concert, Sport, Community, Fair, Culture, Other) | Verify icons are visually distinct (lighter, non-alarming) per client's explicit request in meet4
6 | Two-layer communication (admin directive w/ read-receipt vs org report + free chat) | Not Completed | Two distinct communication layers: high-priority admin directives requiring read-confirmation, and a lighter operational chat between organizations | No Comment/Message model exists at all; only the single title/description on Alert | Design + build a Communique/Message model with a type (directive vs report), read-receipt tracking, and a chat thread tied to each alert
7 | Per-event chat that closes with the event, history retained | Not Completed | A chat scoped to one alert/task; closes (read-only) when the topic is resolved, but stays viewable historically | No chat/thread infrastructure exists | Depends on two-layer communication item - add closedAt/read-only-after-resolve logic to the chat model
8 | Resource Matrix per organization (people/equipment/logistics, time buckets 24h/48h/72h/week) | Needs Change | Each org declares its own resources, categorized, with time-to-availability buckets, inspired by UNHCR Matrix | Resource model exists but is scoped to Gmina, not Organization - no per-org ownership; no time-horizon field at all; ResourceCategory exists but flat, no subcategory/tag structure discussed | Add organizationId FK to Resource; add a time-horizon field/enum (24h/48h/72h/week); revisit category taxonomy with client survey
9 | Resource allocation workflow (declare -> in progress -> confirm delivery -> return-to-pool with delay) | Not Completed | Multi-stage status per resource commitment: declared -> in-transit/in-progress -> delivered-confirmed -> returned; ideally confirmed by the person physically delivering it | ResourceStatus enum is flat: AVAILABLE, RESERVED, IN_USE, DEPLETED - no allocation history, no linkage to a specific need, no delivery confirmation step, no mutation UI/API exists at all | Build full CRUD + allocation state machine; add UI for orgs to add/claim/confirm/return resources
10 | Resource <-> Alert linkage (reconcile allocated resources on close) | Not Completed | Needs declared on an alert are matched against organizations' declared resources; closing an alert prompts what to do with allocated-but-unused resources | No relation between Resource and Alert in the schema at all | Add a Need/ResourceAllocation join model linking Alert <-> Resource/Organization; wire alert-resolve action to reconcile allocations
11 | Resource photo upload (max ~3 images) | Not Completed | Client explicitly asked (meet4) for photo attachments per resource, capped at a few images, at minimum cost of effort | No image upload found for resources | Add image upload (min-cost implementation) once resource CRUD exists
12 | Task board / Kanban (new -> in-progress -> completed, org claim/withdraw) | Not Completed | Kanban-style board; "in-progress" split into "still needs help" vs "fully staffed"; withdrawing must post a visible notice, not disappear silently; closed tasks retained as history | No Task model exists in the schema at all - 0% implemented | Build Task model (states: NEW, IN_PROGRESS_NEEDS_HELP, IN_PROGRESS_STAFFED, COMPLETED), claim/withdraw endpoints, withdrawal-notice logic, Kanban UI
13 | Organization verification workflow (KRS auto-check + recommendations) | Not Completed | New orgs shouldn't be approved by one person; propose KRS lookup + peer recommendation/confirmation system | Organization model has no status/verification field - orgs are created directly and immediately by a single ADMIN via API | Add status (PENDING/VERIFIED/REJECTED) to Organization; design KRS-lookup integration and a lightweight peer-confirmation mechanism
14 | Dual-admin approval for new alerts created by non-admin orgs | Not Completed | An alert created by a local org should be flagged "to be verified" with limited functionality until two admins approve it | AlertStatus has no PENDING_VERIFICATION state; no approval-count field; no distinction between admin-authored vs org-authored alerts | Add pending-verification status + dual-approval counter to Alert; gate certain actions while unverified
15 | Multi-tier role structure (main admin/Fundacja -> verified local lead org -> regular member) | Needs Change | 3-tier hierarchy where verified local orgs get elevated (near-admin) permissions within their scope | Role enum is flat: ADMIN, COORDINATOR, VOLUNTEER; COORDINATOR is gmina-scoped, not an org-tier concept | Extend authorization model with an org-level "lead/verified" tier, or confirm with client that gmina-scoped COORDINATOR already satisfies this need
16 | Per-alert "event coordinator" + transferable coordination | Not Completed | Whoever creates/owns an alert becomes its coordinator with elevated rights just for that alert, transferable to another org via a "transfer coordination" button | Only a plain authorId/creator relation exists on Alert - no elevated per-alert permission, no transfer mechanism | Add per-alert coordinator field + transfer endpoint; extend src/lib/authz.ts with alert-scoped permission checks
17 | Closed, invite-only registration | Completed | Admin creates accounts or sends single-use, email-bound invite links; no open signup | InviteToken model (hashed, expiring, single-use, revocable) + POST /api/admin/invites and /api/admin/users; no public /register route | None
18 | Forced password change on first login | Not Completed | When an admin sets a password directly for a user, that user must change it on first login (raised as an explicit action item in meet4 & meet5) | User.passwordChangedAt exists but is only used to invalidate old sessions, not to force a change flow; no mustChangePassword flag found | Add mustChangePassword boolean; enforce a redirect-to-change-password gate in the login flow
19 | Account lockout policy | Needs Change | "Standard" lockout for MVP is fine, but client explicitly wants an admin-facing reset/unlock button for locked accounts | src/lib/lockout.ts implements 20 failed attempts / 1-hour lockout (Redis + Postgres) - solid, but no admin unlock UI/endpoint exists | Add /api/admin/users/[id]/unlock + button in admin user management UI
20 | Login/audit log visible to admin | Completed | Admin should be able to see who logged into which account and when | LoginAttempt model + AuditLog model, surfaced in src/app/(protected)/admin/logs/ ("Logowania" + audit tabs) | None
21 | reCAPTCHA on login/reset/invite flows | Completed | Bot protection on sensitive forms | src/lib/captcha.ts + Captcha.tsx, wired to RECAPTCHA_SECRET_KEY | None
22 | 2FA / MFA | Completed (as scoped) | Client's own dev advisor explicitly deferred 2FA to the "final security phase," not MVP | Confirmed absent (no 2fa/totp/mfa references) | None for now - correctly out of scope for MVP
23 | Address geocoding + manual GPS coordinate entry | Completed | Typing a street address should auto-locate on map; pasting raw GPS coordinates should also work | src/app/api/geocode (Nominatim) two-way binding in AlertForm.tsx/LocationPicker.tsx; manual lat/lng inputs present; confirmed working per meet5 discussion | None
24 | Map filters (severity/category, 24h/48h/72h time horizon, active vs completed) | Completed | Filter alerts by urgency and by time window, hide completed by default | AlertsMapView.tsx implements all of these | None
25 | Filtering needs "like Allegro" by support category (material/personal/psychological) | Not Completed | Org should be able to filter across all alerts by the type of support needed, independent of event category | Depends on the (currently non-existent) Need/resource-request model - not implemented | Design once the Need/Resource-allocation model exists
26 | Public read-only citizen view | Descoped | Originally requested as MVP (meeting 1), but explicitly postponed by the client in meeting 2's outcome notes | Not implemented - consistent with the client's own descoping decision | No action needed unless client re-raises it
27 | Web-only MVP (no native mobile) | Completed | Client agreed web app is sufficient for MVP; mobile is a post-MVP consideration | App is a Next.js web app only | None
28 | GDPR-minimal data fields (name, email, phone, role, resource/need data only) | Completed | No sensitive personal data fields anywhere in the system | User/Organization models contain only name, contact, role, gmina/org linkage - no sensitive-data fields found | None (re-verify if new fields are added later)